## Sheet1
1. Initial literature review | Initial Literature Review
Project Rational
2. Project rationale
3. Design investigation and identify resources available
4. Develop statistical skills
5. Carry out investigation
6. Learn how to use computer packages
7. Analyse data
8. Write report on investigation (6 month report)
9. Draft questionnaire and identify participants for pilot study
10. Finalise questionnaire identifying methods of statistical analysis
11. Identify target group and carry out pilot study
12. Analyse questionnaire and review pilot study
13. Nine month transfer report
14. Meeting with supervisor
15. Holidays
16. Redraft questionnaire for survey
17. Establishing target group and sampling approach for survey
18. Complete survey
19. Write report on findings (First draft of 18 month report)
20. Final draft of 18 month report
21. First draft of 24 month report, including second investigation
22. Final draft of 24 month report
23. Carry out further research and/or analysis
24. Prepare chapter headings and drafts
25. Complete and submit paper for conference (drafts and completed paper)
26. Job applications and interviews
27. Prepare second drafts of chapters
28. Complete and submit paper to journal
29. Complete and submit final draft of thesis
30. Prepare for Viva

## Sheet2
Project Planning and Preparation
Define research objectives and scope
Conduct literature review on cavitation erosion and Stellite materials
Develop research methodology
Obtain necessary approvals and permissions
Deliverable - Aims & Objectives
Resource Management
Define Resource Requirements
Identification of types of resources needed (e.g., personnel, equipment, materials)
Resource - Personnel
Resource - Equipment
Deliverable - Resource Management
Risk Management
Identification of risks
Identification of Likelihood and Impact of Identified Risks
Identify Risk Mitigation Strategies
Deliverable - Risk Management
Beneficiaries & Stakeholder
Identification of beneficiaries
Identification of stakeholders
Deliverable - Beneficiaries & Stakeholder
Material Preparation
Procure Stellite samples of different compositions
Prepare Stellite samples for testing (e.g., cutting, shaping, polishing)
Characterize Stellite samples (e.g., composition analysis, surface roughness measurement)
Milestone - Sample handover
Experimental Rig Setup
Design cavitation erosion test rig
Review cavitation erosion design - Ahmed Algoburi
Review cavitation erosion design - Dr Rehan Ahmed
Review cavitation erosion design - Dr Mohammed Al-Musleh
Review cavitation erosion design - Muhsin Aykapadattu
Milestone - Acquire equipment for cavitation erosion rig
Structure Assembly
Milestone - Assemble Design
Mounting of Equipment
Milestone - Equipment Mounted
Wiring of Power Cables
Wiring of Signal Cables
Connection of Fluid Cables
Calibrate instrumentation (e.g., ultrasonic transducers, pressure sensors)
Milestone - Equipment Components functional
Integration Testing
Milestone - Stainless steel samples
Cavitation Testing
Conduct baseline cavitation tests on Stellite samples
Monitor erosion progression over time
Collect data on erosion rates, surface morphology changes, and other relevant parameters
Data Analysis
Process experimental data (e.g., erosion depth measurements, surface roughness data)
Fit to parameter models
Analyze cavitation erosion mechanisms and patterns
Material characterization
SEM & EDS - Visit 1
SEM & EDS - Visit 2
SEM & EDS - Visit 3
SEM & EDS - Visit 4
Reporting and Documentation
Create visualizations (e.g., graphs, charts) to illustrate findings
Adapt Literature Review
Milestone - Report - Introduction
Milestone - Report - Methodology
Milestone - Report - Results & Discussion
Milestone - Report - Conclusion
Milestone - Report - Abstract
Presentation
Create presentation materials (e.g., slides)
Practice oral presentation
Publication
Write conference paper
Present research findings at conferences, seminars, or workshops
Write journal paper
Publish research findings in scientific journals or other relevant publications